## Lofthus Website
Lofthus Frukt og Saft
[6 empty] | Legend: |  |  | Estimated Duration | [5 empty] | Actual Duration |  |  |  |  | Percentage Completed
Website Development Checklist | In Charge | Planned Start | Estimated Duration | Actual Duration | Percentage Completed | Week Number
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Information Gathering
Set goal for Lofthus website | PM, IA | 1 | 1 | 1 | 100%
Define target audience | All team members | 1 | 1 | 1 | 100%
Review existing branding strategy | All team members | 2 | 1 | 1 | 100% | bar: Week Number 1 to Week Number 3
Planning Phase
Brand re-strategizing | PM, IA | 3 | 3 | 4 | 75% | bar: Week Number 3 to Week Number 7
Create sitemap sketch | IA, UXD, WD, IA, PM | 5 | 3 | 3 | 66% | bar: Week Number 5 to Week Number 7
Create wireframe and mock-up | UXD, UID, WD, IA, PM | 6 | 3 | 3 | 66% | bar: Week Number 5 to Week Number 9
Design Phase
Create style tiles/mood boards | GD, UXD, UID, IA | 9 | 4 | 5 | 60% | bar: Week Number 9 to Week Number 13
Create different page layouts | UID, UXD, WD, PM | 11 | 4 | 7 | 40% | bar: Week Number 11 to Week Number 17
Review the layouts | QA, IA, WCS,PM | 15 | 3 | 4 | wip | bar: Week Number 13 to Week Number 17
Get client's feedback on layouts/style tiles | CL, PM, IA | 18 | 1 | 2 | wip | bar: Week Number 17 to Week Number 19
Make necessary changes | All design members | 19 | 2 | 2 | wip | bar: Week Number 19 to Week Number 21
Content Gathering and Assembly
Writing Content | WCS, UXD, UID | 21 | 6 | 9 | wip | bar: Week Number 21 to Week Number 29
Photo Ops | GD | 23 | 2 | 3 | wip | bar: Week Number 23 to Week Number 25
Image Editing | GD | 25 | 2 | 2 | wip | bar: Week Number 25 to Week Number 27
Asset creation | GD | 27 | 3 | 5 | wip | bar: Week Number 27 to Week Number 31
Proofreading | QA, IA, WCS,PM | 30 | 3 | 3 | wip | bar: Week Number 29 to Week Number 33
Get all content ready for migration | WCS, UXD, UID | 32 | 4 | 5 | wip | bar: Week Number 31 to Week Number 35
Coding
Build and deploy website | WD, UXD, UID, WCS | 36 | 8 | bar: Week Number 1; Week Number 35 to Week Number 43
Add special features and interactivity | WD, UXD, UID, WCS | 42 | 6 | bar: Week Number 41 to Week Number 47
SEO for the website | WD, UXD, UID, WCS | 48 | 3 | bar: Week Number 1; Week Number 47 to Week Number 51
Testing, Review and Launch
Test created website | QA, IA, WCS,PM | 52 | 2 | bar: Week Number 1; Week Number 51 to Week Number 53
Upload website to server | SA, WD, IA, PM | 53 | 2 | bar: Week Number 51 to Week Number 53
Final testing and launch of website | All team members | 54 | 2 | bar: Week Number 1; Week Number 53 to Week Number 55
Team Member Roles: | Abbreviation
Project Manager | PM
Information Architect | IA
User Experience Designer | UXD
User Interface Designer | UID
Web Developer | WD
Web Content Specialist | WCS
Quality Assurance Tester | QA
Server Administrator | SA
Graphic Designer | GD
Client | CL